## Backlog-FULL
LOC Evaluation for OrcaXCare (Full Backlog)
Columns A–I: features/functions only (for RDS use cases). No DevOps/QA/validators. Column "Iter (draft)": suggested split — adjust as a team.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Iter (draft) | LOC | Complexity | Quality | SRS | SDS
1 | Login | Authentication | User enters email and password; system validates and returns session token; redirect to role dashboard. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
2 | Logout | Authentication | End session; clear token; return to public login page. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
3 | Forgot Password | Authentication | Request reset link by email; set new password via token page. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
4 | Register Account | Authentication | New patient registers with email password and profile basics; account pending until email verified. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
5 | Verify Email | Authentication | User opens link from email; system activates account or shows expired token message. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
6 | Change Password | Authentication | Logged-in user updates password after verifying current password. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
7 | View Accounts List | Account Management | Admin views paginated users; filter by role and status; search by name or email. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
8 | View Account Detail | Account Management | Admin views one user: role status linked doctor or patient profile. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
9 | Create Account | Account Management | Admin creates staff account (doctor/admin); assign role and initial password. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
10 | Update Account | Account Management | Admin edits user contact fields; prevent duplicate email. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
11 | Grant or Change Role | Account Management | Admin changes user role; permissions update immediately. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
12 | Deactivate Account | Account Management | Admin soft-deactivates account; user cannot log in; data retained. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
13 | Restore Account | Account Management | Admin reactivates deactivated account. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
14 | Create Specialty | Specialty Management | Admin adds medical specialty name and description. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
15 | View Specialties List | Specialty Management | Admin or patient views list of specialties for filter and assignment. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
16 | Update Specialty | Specialty Management | Admin edits specialty information. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
17 | Delete Specialty | Specialty Management | Admin removes specialty if not linked to active doctors. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
18 | Create Department | Department Management | Admin adds clinic department: name location contact. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
19 | View Departments List | Department Management | List departments with doctor count and status. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
20 | Update Department | Department Management | Admin edits department details or deactivates. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
21 | Create Clinic Room | Facility Management | Admin adds examination room: code floor equipment notes. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
22 | View Clinic Rooms List | Facility Management | List rooms by department; show availability flag. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
23 | Update Clinic Room | Facility Management | Admin edits room information. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
24 | Create Doctor | Doctor Management | Admin registers doctor profile and linked login: specialty department license bio. | ThangNDCE180608 | To Do | 1 | 120 | Medium | High
25 | View Doctors List | Doctor Management | List doctors with filters by specialty department name; active only for patients. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
26 | View Doctor Detail | Doctor Management | View full doctor profile ratings summary and schedule overview. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
27 | Update Doctor | Doctor Management | Admin edits doctor professional and account linkage. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
28 | Deactivate Doctor | Doctor Management | Hide doctor from search and booking; keep history. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
29 | Import Doctors Excel | Doctor Management | Bulk upload doctors from spreadsheet; validation report per row. | KhoaNNCE181612 | To Do | 1 | 120 | Medium | High
30 | Export Doctors Excel | Doctor Management | Download doctor list with specialty and department. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
31 | View Portal Home | Patient Portal | Landing page: services featured doctors health news call-to-action login register. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
32 | Search Doctors | Patient Portal | Patient searches by name specialty symptom keyword; paginated results. | ThangDQCE182036 | To Do | 1 | 120 | Medium | High
33 | View Doctor Public Profile | Patient Portal | Read-only doctor card from search before booking. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
34 | View Own Profile | Patient Profile | Patient views personal demographics emergency contact and avatar. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
35 | Update Own Profile | Patient Profile | Patient edits allowed profile fields with validation. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
36 | Upload Profile Avatar | Patient Profile | Patient uploads profile photo; preview and save. | ThangDQCE182036 | To Do | 1 | 120 | Medium | High
37 | View Patients List | Patient Profile | Admin lists patients; search by name phone; pagination. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
38 | View Patient Detail | Patient Profile | Admin views patient demographics and registration info. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
39 | Create Patient | Patient Profile | Admin registers patient record on behalf of walk-in or staff entry. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
40 | Update Patient Profile | Patient Profile | Admin corrects patient record fields. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
41 | Deactivate Patient | Patient Profile | Soft-delete patient; hide from active lists; retain history. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
42 | Manage Doctor Work Shifts | Schedule Management | Admin or doctor defines working hours and capacity per day. | TruongNTCE180140 | To Do | 2 | 120 | Medium | High
43 | View Doctor Schedule Calendar | Schedule Management | Calendar grid of available and booked slots for one doctor. | TruongNTCE180140 | To Do | 2 | 120 | Medium | High
44 | Generate Appointment Slots | Schedule Management | System creates non-overlapping timeslots from shifts; block holidays. | TruongNTCE180140 | To Do | 2 | 120 | Medium | High
45 | Block Timeslot | Schedule Management | Admin or doctor marks slot unavailable without deleting series. | TruongNTCE180140 | To Do | 2 | 60 | Simple | High
46 | Book Appointment | Appointment Booking | Patient wizard: choose specialty doctor timeslot; see price summary; confirm booking. | ThangDQCE182036 | To Do | 2 | 120 | Medium | High
47 | Prevent Double Booking | Appointment Booking | System rejects slot already reserved; show alternative slots. | ThangDQCE182036 | To Do | 2 | 120 | Medium | High
48 | View My Appointments | Appointment Booking | Patient lists upcoming and past appointments with status badges. | ThangDQCE182036 | To Do | 2 | 60 | Simple | High
49 | View Appointment Detail | Appointment Booking | Patient or staff views appointment info QR code payment status. | ThangDQCE182036 | To Do | 2 | 60 | Simple | High
50 | Cancel Appointment | Appointment Booking | Patient cancels before deadline; show refund policy message. | ThangDQCE182036 | To Do | 2 | 60 | Simple | High
51 | View Wallet Balance | Wallet | Patient views current wallet balance on dashboard. | TanhNTCE182341 | To Do | 2 | 60 | Simple | High
52 | Top Up Wallet | Wallet | Patient adds funds via online payment gateway sandbox. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
53 | Pay Booking with Wallet | Wallet | Deduct booking fee from wallet at confirmation; show receipt. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
54 | Refund to Wallet on Cancel | Wallet | Credit eligible amount to wallet when appointment cancelled in policy window. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
55 | Online Payment Checkout | Payment | Redirect to VNPay/Momo sandbox for appointment or top-up; return result page. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
56 | View Transaction History | Payment | Patient lists top-up payment refund entries with date filters. | TanhNTCE182341 | To Do | 2 | 60 | Simple | High
57 | Manage Health Insurance Card | Health Insurance | Patient stores policy number validity and coverage percent. | TanhNTCE182341 | To Do | 2 | 60 | Simple | High
58 | Apply Insurance Discount | Health Insurance | Show reduced booking price when valid insurance on file. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
59 | Scan Insurance Card OCR | Health Insurance | Optional upload card image to pre-fill policy fields. | TanhNTCE182341 | To Do | 3 | 120 | Medium | Medium
60 | View Today Appointments | Doctor Workspace | Doctor sees list of patients scheduled for selected day. | ThangNDCE180608 | To Do | 2 | 60 | Simple | High
61 | Join Live Waiting Queue | Queue Management | Patient sees real-time queue number and estimated wait on screen. | TruongNTCE180140 | To Do | 3 | 120 | Medium | High
62 | Call Next Patient | Queue Management | Doctor advances queue; patient display updates in real time. | TruongNTCE180140 | To Do | 3 | 120 | Medium | High
63 | View Queue Board | Queue Management | Waiting room display of current and next ticket numbers. | TruongNTCE180140 | To Do | 3 | 60 | Simple | High
64 | View Patient EMR Timeline | Electronic Medical Record | Doctor opens chronological encounters diagnoses and notes for patient. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
65 | Create Medical Encounter | Electronic Medical Record | Doctor starts visit linked to appointment; record vitals and notes. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
66 | Add Diagnosis | Electronic Medical Record | Doctor selects ICD code and diagnosis text for encounter. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
67 | Search ICD Catalog | Electronic Medical Record | Autocomplete search standard disease codes when diagnosing. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
68 | Upload Medical Image | Medical Imaging | Doctor uploads X-ray or scan linked to encounter; view thumbnail list. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
69 | View Medical Imaging Gallery | Medical Imaging | Doctor or authorized staff browses patient imaging history. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
70 | Create Prescription | Prescription | Doctor adds medicines dosage duration to encounter; validate stock availability. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
71 | View Prescription Detail | Prescription | Patient or doctor views prescription line items and instructions. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
72 | Export Prescription PDF | Prescription | Generate downloadable PDF with clinic letterhead and doctor signature block. | KhoaNNCE181612 | To Do | 3 | 120 | Medium | High
73 | Display Prescription QR Code | Prescription | Show QR on prescription for pharmacy verification. | KhoaNNCE181612 | To Do | 3 | 60 | Simple | High
74 | Verify Prescription QR | Prescription | Staff scans QR to confirm prescription validity and status. | KhoaNNCE181612 | To Do | 3 | 60 | Simple | High
75 | View Pharmacy Inventory | Pharmacy Inventory | Admin lists medicines SKU quantity batch expiry; highlight low stock. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
76 | Record Stock Inbound | Pharmacy Inventory | Admin adds incoming medicine batch to inventory. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
77 | Record Stock Outbound | Pharmacy Inventory | Deduct stock when prescription dispensed or adjusted. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
78 | View Low Stock Alerts | Pharmacy Inventory | Dashboard of items below threshold or nearing expiry. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
79 | Add Favorite Doctor | Patient Portal | Patient saves doctor to favorites for quick rebooking. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
80 | View Favorite Doctors | Patient Portal | Patient opens list of saved doctors. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
81 | Remove Favorite Doctor | Patient Portal | Patient removes doctor from favorites. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
82 | Submit Doctor Review | Reviews | Patient rates doctor after completed visit; optional comment. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
83 | View Doctor Reviews | Reviews | Public or patient view of aggregated ratings and comments. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
84 | Subscribe Web Push Notifications | Notifications | Patient or doctor opts in to browser notifications. | ThangDQCE182036 | To Do | 3 | 60 | Simple | Medium
85 | Receive Appointment Reminder | Notifications | System sends reminder before appointment time. | ThangDQCE182036 | To Do | 3 | 60 | Simple | Medium
86 | Receive Results Ready Notification | Notifications | Notify patient when lab or prescription PDF is available. | ThangDQCE182036 | To Do | 3 | 60 | Simple | Medium
87 | Submit Complaint | Complaints | Patient submits feedback or complaint with category and description. | ThangDQCE182036 | To Do | 4 | 60 | Simple | High
88 | View My Complaints | Complaints | Patient tracks complaint status and admin responses. | ThangDQCE182036 | To Do | 4 | 60 | Simple | High
89 | Manage Complaints | Complaints | Admin lists complaints; assign status resolved or in progress. | KhoaNNCE181612 | To Do | 4 | 60 | Simple | High
90 | View Revenue Report | Reports | Admin views revenue charts by day week month; filter branch and doctor. | KhoaNNCE181612 | To Do | 4 | 120 | Medium | High
91 | Export Revenue Report | Reports | Download revenue summary to Excel or PDF. | KhoaNNCE181612 | To Do | 4 | 60 | Simple | High
92 | View Clinic Branches on Map | Clinic Locator | Patient views branch locations on map and directions link. | ThangDQCE182036 | To Do | 4 | 60 | Simple | Medium
93 | View Branch List | Clinic Locator | List clinic addresses hours and contact phone. | ThangDQCE182036 | To Do | 4 | 60 | Simple | Medium
94 | Send Appointment Email | Notifications | Email confirmation and results to patient after booking or visit. | KhoaNNCE181612 | To Do | 4 | 60 | Simple | Medium

## Iter1
LOC Evaluation for OrcaXCare (Iteration 1)
Sprint Goal: Core auth, RBAC, master data (specialty, department, doctor), patient profile, portal home and doctor search.
1 | Login | Authentication | User enters email and password; system validates and returns session token; redirect to role dashboard. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
2 | Logout | Authentication | End session; clear token; return to public login page. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
3 | Forgot Password | Authentication | Request reset link by email; set new password via token page. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
4 | Register Account | Authentication | New patient registers with email password and profile basics; account pending until email verified. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
5 | Verify Email | Authentication | User opens link from email; system activates account or shows expired token message. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
6 | Change Password | Authentication | Logged-in user updates password after verifying current password. | TruongNTCE180140 | To Do | 1 | 60 | Simple | High
7 | View Accounts List | Account Management | Admin views paginated users; filter by role and status; search by name or email. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
8 | View Account Detail | Account Management | Admin views one user: role status linked doctor or patient profile. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
9 | Create Account | Account Management | Admin creates staff account (doctor/admin); assign role and initial password. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
10 | Update Account | Account Management | Admin edits user contact fields; prevent duplicate email. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
11 | Grant or Change Role | Account Management | Admin changes user role; permissions update immediately. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
12 | Deactivate Account | Account Management | Admin soft-deactivates account; user cannot log in; data retained. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
13 | Restore Account | Account Management | Admin reactivates deactivated account. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
14 | Create Specialty | Specialty Management | Admin adds medical specialty name and description. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
15 | View Specialties List | Specialty Management | Admin or patient views list of specialties for filter and assignment. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
16 | Update Specialty | Specialty Management | Admin edits specialty information. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
17 | Delete Specialty | Specialty Management | Admin removes specialty if not linked to active doctors. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
18 | Create Department | Department Management | Admin adds clinic department: name location contact. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
19 | View Departments List | Department Management | List departments with doctor count and status. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
20 | Update Department | Department Management | Admin edits department details or deactivates. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
21 | Create Clinic Room | Facility Management | Admin adds examination room: code floor equipment notes. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
22 | View Clinic Rooms List | Facility Management | List rooms by department; show availability flag. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
23 | Update Clinic Room | Facility Management | Admin edits room information. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
24 | Create Doctor | Doctor Management | Admin registers doctor profile and linked login: specialty department license bio. | ThangNDCE180608 | To Do | 1 | 120 | Medium | High
25 | View Doctors List | Doctor Management | List doctors with filters by specialty department name; active only for patients. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
26 | View Doctor Detail | Doctor Management | View full doctor profile ratings summary and schedule overview. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
27 | Update Doctor | Doctor Management | Admin edits doctor professional and account linkage. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
28 | Deactivate Doctor | Doctor Management | Hide doctor from search and booking; keep history. | ThangNDCE180608 | To Do | 1 | 60 | Simple | High
29 | Import Doctors Excel | Doctor Management | Bulk upload doctors from spreadsheet; validation report per row. | KhoaNNCE181612 | To Do | 1 | 120 | Medium | High
30 | Export Doctors Excel | Doctor Management | Download doctor list with specialty and department. | KhoaNNCE181612 | To Do | 1 | 60 | Simple | High
31 | View Portal Home | Patient Portal | Landing page: services featured doctors health news call-to-action login register. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
32 | Search Doctors | Patient Portal | Patient searches by name specialty symptom keyword; paginated results. | ThangDQCE182036 | To Do | 1 | 120 | Medium | High
33 | View Doctor Public Profile | Patient Portal | Read-only doctor card from search before booking. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
34 | View Own Profile | Patient Profile | Patient views personal demographics emergency contact and avatar. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
35 | Update Own Profile | Patient Profile | Patient edits allowed profile fields with validation. | ThangDQCE182036 | To Do | 1 | 60 | Simple | High
36 | Upload Profile Avatar | Patient Profile | Patient uploads profile photo; preview and save. | ThangDQCE182036 | To Do | 1 | 120 | Medium | High
37 | View Patients List | Patient Profile | Admin lists patients; search by name phone; pagination. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
38 | View Patient Detail | Patient Profile | Admin views patient demographics and registration info. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
39 | Create Patient | Patient Profile | Admin registers patient record on behalf of walk-in or staff entry. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
40 | Update Patient Profile | Patient Profile | Admin corrects patient record fields. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High
41 | Deactivate Patient | Patient Profile | Soft-delete patient; hide from active lists; retain history. | TanhNTCE182341 | To Do | 1 | 60 | Simple | High

## Iter2
LOC Evaluation for OrcaXCare (Iteration 2)
Sprint Goal: Scheduling, appointment booking, wallet, online payment, insurance basics.
1 | Login | Authentication | User enters email and password; system validates and returns session token; redirect to role dashboard. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
42 | Manage Doctor Work Shifts | Schedule Management | Admin or doctor defines working hours and capacity per day. | TruongNTCE180140 | To Do | 2 | 120 | Medium | High
43 | View Doctor Schedule Calendar | Schedule Management | Calendar grid of available and booked slots for one doctor. | TruongNTCE180140 | To Do | 2 | 120 | Medium | High
44 | Generate Appointment Slots | Schedule Management | System creates non-overlapping timeslots from shifts; block holidays. | TruongNTCE180140 | To Do | 2 | 120 | Medium | High
45 | Block Timeslot | Schedule Management | Admin or doctor marks slot unavailable without deleting series. | TruongNTCE180140 | To Do | 2 | 60 | Simple | High
46 | Book Appointment | Appointment Booking | Patient wizard: choose specialty doctor timeslot; see price summary; confirm booking. | ThangDQCE182036 | To Do | 2 | 120 | Medium | High
47 | Prevent Double Booking | Appointment Booking | System rejects slot already reserved; show alternative slots. | ThangDQCE182036 | To Do | 2 | 120 | Medium | High
48 | View My Appointments | Appointment Booking | Patient lists upcoming and past appointments with status badges. | ThangDQCE182036 | To Do | 2 | 60 | Simple | High
49 | View Appointment Detail | Appointment Booking | Patient or staff views appointment info QR code payment status. | ThangDQCE182036 | To Do | 2 | 60 | Simple | High
50 | Cancel Appointment | Appointment Booking | Patient cancels before deadline; show refund policy message. | ThangDQCE182036 | To Do | 2 | 60 | Simple | High
51 | View Wallet Balance | Wallet | Patient views current wallet balance on dashboard. | TanhNTCE182341 | To Do | 2 | 60 | Simple | High
52 | Top Up Wallet | Wallet | Patient adds funds via online payment gateway sandbox. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
53 | Pay Booking with Wallet | Wallet | Deduct booking fee from wallet at confirmation; show receipt. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
54 | Refund to Wallet on Cancel | Wallet | Credit eligible amount to wallet when appointment cancelled in policy window. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
55 | Online Payment Checkout | Payment | Redirect to VNPay/Momo sandbox for appointment or top-up; return result page. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
56 | View Transaction History | Payment | Patient lists top-up payment refund entries with date filters. | TanhNTCE182341 | To Do | 2 | 60 | Simple | High
57 | Manage Health Insurance Card | Health Insurance | Patient stores policy number validity and coverage percent. | TanhNTCE182341 | To Do | 2 | 60 | Simple | High
58 | Apply Insurance Discount | Health Insurance | Show reduced booking price when valid insurance on file. | TanhNTCE182341 | To Do | 2 | 120 | Medium | High
60 | View Today Appointments | Doctor Workspace | Doctor sees list of patients scheduled for selected day. | ThangNDCE180608 | To Do | 2 | 60 | Simple | High

## Iter3
LOC Evaluation for OrcaXCare (Iteration 3)
Sprint Goal: Queue, EMR, prescriptions, pharmacy inventory, imaging, reviews.
1 | Login | Authentication | User enters email and password; system validates and returns session token; redirect to role dashboard. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
59 | Scan Insurance Card OCR | Health Insurance | Optional upload card image to pre-fill policy fields. | TanhNTCE182341 | To Do | 3 | 120 | Medium | Medium
61 | Join Live Waiting Queue | Queue Management | Patient sees real-time queue number and estimated wait on screen. | TruongNTCE180140 | To Do | 3 | 120 | Medium | High
62 | Call Next Patient | Queue Management | Doctor advances queue; patient display updates in real time. | TruongNTCE180140 | To Do | 3 | 120 | Medium | High
63 | View Queue Board | Queue Management | Waiting room display of current and next ticket numbers. | TruongNTCE180140 | To Do | 3 | 60 | Simple | High
64 | View Patient EMR Timeline | Electronic Medical Record | Doctor opens chronological encounters diagnoses and notes for patient. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
65 | Create Medical Encounter | Electronic Medical Record | Doctor starts visit linked to appointment; record vitals and notes. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
66 | Add Diagnosis | Electronic Medical Record | Doctor selects ICD code and diagnosis text for encounter. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
67 | Search ICD Catalog | Electronic Medical Record | Autocomplete search standard disease codes when diagnosing. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
68 | Upload Medical Image | Medical Imaging | Doctor uploads X-ray or scan linked to encounter; view thumbnail list. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
69 | View Medical Imaging Gallery | Medical Imaging | Doctor or authorized staff browses patient imaging history. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
70 | Create Prescription | Prescription | Doctor adds medicines dosage duration to encounter; validate stock availability. | ThangNDCE180608 | To Do | 3 | 120 | Medium | High
71 | View Prescription Detail | Prescription | Patient or doctor views prescription line items and instructions. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
72 | Export Prescription PDF | Prescription | Generate downloadable PDF with clinic letterhead and doctor signature block. | KhoaNNCE181612 | To Do | 3 | 120 | Medium | High
73 | Display Prescription QR Code | Prescription | Show QR on prescription for pharmacy verification. | KhoaNNCE181612 | To Do | 3 | 60 | Simple | High
74 | Verify Prescription QR | Prescription | Staff scans QR to confirm prescription validity and status. | KhoaNNCE181612 | To Do | 3 | 60 | Simple | High
75 | View Pharmacy Inventory | Pharmacy Inventory | Admin lists medicines SKU quantity batch expiry; highlight low stock. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
76 | Record Stock Inbound | Pharmacy Inventory | Admin adds incoming medicine batch to inventory. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
77 | Record Stock Outbound | Pharmacy Inventory | Deduct stock when prescription dispensed or adjusted. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
78 | View Low Stock Alerts | Pharmacy Inventory | Dashboard of items below threshold or nearing expiry. | ThangNDCE180608 | To Do | 3 | 60 | Simple | High
79 | Add Favorite Doctor | Patient Portal | Patient saves doctor to favorites for quick rebooking. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
80 | View Favorite Doctors | Patient Portal | Patient opens list of saved doctors. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
81 | Remove Favorite Doctor | Patient Portal | Patient removes doctor from favorites. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
82 | Submit Doctor Review | Reviews | Patient rates doctor after completed visit; optional comment. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
83 | View Doctor Reviews | Reviews | Public or patient view of aggregated ratings and comments. | ThangDQCE182036 | To Do | 3 | 60 | Simple | High
84 | Subscribe Web Push Notifications | Notifications | Patient or doctor opts in to browser notifications. | ThangDQCE182036 | To Do | 3 | 60 | Simple | Medium
85 | Receive Appointment Reminder | Notifications | System sends reminder before appointment time. | ThangDQCE182036 | To Do | 3 | 60 | Simple | Medium
86 | Receive Results Ready Notification | Notifications | Notify patient when lab or prescription PDF is available. | ThangDQCE182036 | To Do | 3 | 60 | Simple | Medium

## Iter4
LOC Evaluation for OrcaXCare (Iteration 4)
Sprint Goal: Complaints, revenue reports, branch locator, email notifications.
1 | Login | Authentication | User enters email and password; system validates and returns session token; redirect to role dashboard. | TruongNTCE180140 | To Do | 1 | 120 | Medium | High
87 | Submit Complaint | Complaints | Patient submits feedback or complaint with category and description. | ThangDQCE182036 | To Do | 4 | 60 | Simple | High
88 | View My Complaints | Complaints | Patient tracks complaint status and admin responses. | ThangDQCE182036 | To Do | 4 | 60 | Simple | High
89 | Manage Complaints | Complaints | Admin lists complaints; assign status resolved or in progress. | KhoaNNCE181612 | To Do | 4 | 60 | Simple | High
90 | View Revenue Report | Reports | Admin views revenue charts by day week month; filter branch and doctor. | KhoaNNCE181612 | To Do | 4 | 120 | Medium | High
91 | Export Revenue Report | Reports | Download revenue summary to Excel or PDF. | KhoaNNCE181612 | To Do | 4 | 60 | Simple | High
92 | View Clinic Branches on Map | Clinic Locator | Patient views branch locations on map and directions link. | ThangDQCE182036 | To Do | 4 | 60 | Simple | Medium
93 | View Branch List | Clinic Locator | List clinic addresses hours and contact phone. | ThangDQCE182036 | To Do | 4 | 60 | Simple | Medium
94 | Send Appointment Email | Notifications | Email confirmation and results to patient after booking or visit. | KhoaNNCE181612 | To Do | 4 | 60 | Simple | Medium