## Epics
Parent_ID | Screen_Function | Epic_Feature | Description | In_Charge | Status | Sprint | SRS | SDS | LOC | Code_Demo_Comments | Complexity | Quality | Subtask_count | Subtask_LOC_sum
1 | Queue screen (patient + doctor) | Real-time queue | Doctor clicks Next; Socket.io syncs the queue number to the patient screen immediately. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 180 | Demo two browsers in the same session. | High |  | 3 | 180
2 | Admin / Doctor — Schedule | Appointment slot scheduling | Algorithm generates time slots from doctor shifts; prevents duplicate internal slots. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 200 | Show slot grid by day. | High |  | 3 | 200
3 | Server — API architecture | Architecture & auth middleware | Express boilerplate; layered JWT middleware; centralized error handling. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 120 | Sample Postman collection. | Medium |  | 3 | 120
4 | Portal + API | Registration & login | Accounts; password hashing; safe token issue and revocation. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 150 | Short video of registration flow. | Medium |  | 3 | 150
5 | Portal — Find doctor | Smart search | Search by name; specialty; symptom hints (regex / index). | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 100 | A few sample queries. | Medium |  | 3 | 100
6 | Portal — Profile | Personal profile management | Update info; avatar; basic medical history. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 90 | Validated form. | Standard |  | 3 | 90
7 | Payments | Online payment | MoMo or VNPay sandbox integration; callback handling. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 220 | Successful test transaction. | High |  | 3 | 220
8 | Wallet + API | Internal medical wallet | Balance; atomic credit/debit; non-negative balance. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 180 | Unit tests for wallet flow. | High |  | 3 | 180
9 | Portal — Health insurance | Health insurance management | Store insurance card; optional OCR; apply discount per rules. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 160 | Cases with and without insurance. | Medium |  | 3 | 160
10 | Portal — History | Transaction history | List of top-ups and spends; filter by date and type. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 110 | Optional CSV export. | Medium |  | 3 | 110
11 | Booking + Wallet | Automatic refund | Cancel before deadline; refund to wallet per policy. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 130 | Two cancel cases: inside and outside policy window. | Medium |  | 3 | 130
12 | Server — RBAC | RBAC authorization | Medical record view policy; stock approval; consistent route guards. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 100 | Permission matrix. | Standard |  | 3 | 100
13 | Doctor — EMR | EMR medical record | Diagnosis timeline; quick lookup by patient. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 240 | Three sample encounters. | High |  | 3 | 240
14 | Admin — Stock | Pharmacy stock management | Stock in/out; low-stock and expiry warnings. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 200 | Stock table view. | High |  | 3 | 200
15 | Admin — Staff | Doctor management | CRUD medical staff; departments; specialties. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 160 | CRUD demo. | Medium |  | 3 | 160
16 | Doctor — Imaging | Imaging library | Cloudinary upload for X-ray / MRI; album per visit. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 140 | Upload one image. | Medium |  | 3 | 140
17 | Admin — Facilities | Clinic room management | Functional rooms; equipment per room. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 120 | Room layout diagram. | Standard |  | 3 | 120
18 | Admin — Catalog | ICD catalog | Standard disease codes; search when entering diagnosis. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 100 | Sample CSV import. | Standard |  | 3 | 100
19 | Portal — Booking | Booking flow | Four steps: Department → Doctor → Time → Payment. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 220 | Screen recording. | High |  | 3 | 220
20 | API Booking | Double-booking check | Prevent booking a slot already taken. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 120 | Concurrent test with two users. | High |  | 3 | 120
21 | Portal — Home | Patient home page | Featured services; featured doctors; health news. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 130 | Responsive landing. | Medium |  | 3 | 130
22 | Notifications | Web Push | Appointment reminders; lab results available. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 140 | Subscribe in Chrome. | Medium |  | 3 | 140
23 | Portal — Review | Doctor rating | After visit; rating and comment. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 100 | One sample review. | Medium |  | 3 | 100
24 | Portal — Favorites | Preferred doctor list | Shortcuts for faster re-booking. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | Add/remove favorite. | Standard |  | 2 | 80
25 | Admin — Reports | Revenue report | MongoDB aggregation + Chart.js charts. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 180 | Monthly dashboard. | High |  | 3 | 180
26 | Doctor — Prescriptions | Prescription PDF export | Medical-standard template from DB data. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 160 | Sample PDF file. | High |  | 3 | 160
27 | Portal + Kiosk | QR verification | QR on prescription and record for scan verification. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 100 | Scan with phone camera. | Medium |  | 3 | 100
28 | System — Email | Automated email | SMTP for visit results, prescription, follow-up. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 120 | MailHog or log output. | Medium |  | 3 | 120
29 | Portal — Maps | Branch map | Maps API directions to clinic. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 100 | One map marker. | Medium |  | 3 | 100
30 | Admin + Portal | Complaint handling | Intake; processing status. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 110 | Ticket workflow. | Standard |  | 3 | 110
31 | Server — Quality | Input validation | Joi or Zod on main APIs. | Team | To Do | 1 | SRS § | SDS § | 150 | Example 400 error response. | Medium |  | 3 | 150
32 | Server — Quality | Unified error handling | Error codes; messages; stack traces logged dev-only. | Team | To Do | 1 | SRS § | SDS § | 80 | Postman error response shape. | Medium |  | 3 | 80
33 | DevOps | Seed & light migration | Script to seed sample ICD codes, users, and clinics. | Team | To Do | 1 | SRS § | SDS § | 60 | npm run seed. | Standard |  | 2 | 60
34 | Docs | Short API contract | OpenAPI or endpoint table for the team. | Team | To Do | 1 | SRS § | SDS § | 40 | Link in README. | Standard |  | 2 | 40
35 | QA | Supertest smoke | Minimal path: health, auth, booking, wallet. | Team | To Do | 4 | SRS § | SDS § | 100 | CI runs tests. | Medium |  | 3 | 100

## All
# | Parent_ID | Screen_Function | Feature | Description | In_Charge | Status | Sprint | SRS | SDS | LOC | Code_Demo_Comments | Complexity | Quality
1 | 1 | Queue screen (patient + doctor) | Queue session & ticket API | REST: open session, issue ticket, persist current number. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 60 | Postman CRUD session + ticket. | Medium
2 | 1 | Queue screen (patient + doctor) | Patient queue display | Waiting-room UI; subscribe to updates (Socket or polling fallback). | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 70 | Number changes without refresh. | Medium
3 | 1 | Queue screen (patient + doctor) | Doctor Next + Socket.io broadcast | Doctor action advances queue; emit room event to patients. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 50 | Two browsers stay in sync. | High
4 | 2 | Admin / Doctor — Schedule | Shift / workday model | Link doctors to working hours and branch capacity. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 70 | Seed shifts visible in DB. | Medium
5 | 2 | Admin / Doctor — Schedule | Slot generation service | Generate non-overlapping slots from shifts; API for grid. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 70 | JSON grid for one week. | High
6 | 2 | Admin / Doctor — Schedule | Admin/Doctor slot calendar UI | Day/week grid; block invalid edits. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 60 | UI shows slot grid by day. | High
7 | 3 | Server — API architecture | Express structure | Routes/controllers/services layout; mount routers. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 45 | Folder tree matches SDS. | Medium
8 | 3 | Server — API architecture | Cross-cutting middleware | CORS, request logging, centralized error wrapper stub. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 45 | Logs show request id. | Medium
9 | 3 | Server — API architecture | JWT middleware scaffold + /health | Optional verify hook; GET /health + Mongo ping. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 30 | Health returns 200 when DB up. | Medium
10 | 4 | Portal + API | Register API | Validate payload; hash password; create user + role. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 55 | Invalid email returns 400. | Medium
11 | 4 | Portal + API | Login + JWT issue | Compare hash; sign access token; optional refresh stub. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 55 | Postman returns Bearer token. | Medium
12 | 4 | Portal + API | Client login/register UI | Forms, client validation, store token, redirect by role. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 40 | Short screen capture of flow. | Medium
13 | 5 | Portal — Find doctor | Doctor search API | Filters: name, specialty, branch; pagination. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 35 | curl/Postman sample queries. | Medium
14 | 5 | Portal — Find doctor | Symptom / keyword index | Regex or text index for hints; debounced suggest endpoint. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 40 | Typeahead demo. | Medium
15 | 5 | Portal — Find doctor | Patient portal search page | List + filters UI wired to API. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 25 | UI matches wireframe. | Standard
16 | 6 | Portal — Profile | Profile GET/PATCH API | Own-profile only; partial updates. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 35 | 403 for other users’ ids. | Medium
17 | 6 | Portal — Profile | Avatar upload | Multipart or URL field; size/type validation. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 30 | Avatar updates in header. | Medium
18 | 6 | Portal — Profile | Profile form UI | React form + schema validation + success toast. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 25 | Validated form demo. | Standard
19 | 7 | Payments | Payment provider config | MoMo/VNPay sandbox keys; create payment request DTO. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 80 | Sandbox intent created. | High
20 | 7 | Payments | Callback / webhook handler | Verify signature; idempotent update booking/wallet. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 80 | Replay callback once safely. | High
21 | 7 | Payments | Payment UI + test path | Redirect or QR step; show success/failure. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 60 | One successful sandbox transaction. | High
22 | 8 | Wallet + API | Wallet model & invariants | Balance field; non-negative rule at schema/service. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 70 | Unit: cannot go below zero. | High
23 | 8 | Wallet + API | Credit/debit operations | Mongo transaction or equivalent; audit lines. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 70 | Concurrent debits handled. | High
24 | 8 | Wallet + API | Wallet UI + API wiring | Show balance; list last movements on dashboard. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | UI matches balance after op. | Medium
25 | 9 | Portal — Health insurance | Insurance card CRUD | Store policy number, dates, coverage percent. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 55 | Create + read card. | Medium
26 | 9 | Portal — Health insurance | OCR hook (optional) | Upload image URL; stub or external OCR parse. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 55 | Parsed fields editable. | Medium
27 | 9 | Portal — Health insurance | Billing discount rule | Apply coverage when quoting booking price. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 50 | With/without insurance cases. | Medium
28 | 10 | Portal — History | Transactions list API | Paging, sort by date desc. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Page 2 works. | Medium
29 | 10 | Portal — History | Filters | By date range and type (top-up, payment, refund). | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Filtered JSON. | Medium
30 | 10 | Portal — History | Portal history view | Table + optional CSV export button. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 30 | Export optional. | Medium
31 | 11 | Booking + Wallet | Cancel policy engine | Deadline rules per appointment type. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 45 | Unit tests inside/outside window. | Medium
32 | 11 | Booking + Wallet | Wallet refund credit | Atomic credit linked to cancellation reason. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 45 | Balance increases correctly. | Medium
33 | 11 | Booking + Wallet | Cancel UI flows | Patient cancels; shows refund message. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Two demo cases. | Medium
34 | 12 | Server — RBAC | Permission matrix constants | Role → allowed actions map in code. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 35 | Table in README or MD. | Standard
35 | 12 | Server — RBAC | requireRole middleware | Composable guards for routes. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 40 | 403 on wrong role. | Medium
36 | 12 | Server — RBAC | Resource ownership checks | EMR/stock examples; tests for happy/deny. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 25 | Matrix demo. | Standard
37 | 13 | Doctor — EMR | Encounter CRUD | Create/list encounters by patient; link appointment. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 90 | Three encounters in DB. | High
38 | 13 | Doctor — EMR | Diagnosis entries | Add DX per encounter; ICD ref optional. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 90 | Timeline sorted by date. | High
39 | 13 | Doctor — EMR | Doctor EMR UI | Timeline + patient search + encounter detail panel. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 60 | Click-through demo. | High
40 | 14 | Admin — Stock | Stock & movement models | Medicine SKU, quantity, batch/expiry fields. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 70 | Models in Mongoose. | High
41 | 14 | Admin — Stock | Inbound/outbound flows | Adjust stock; link outbound to prescription later. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 70 | Stock delta correct. | High
42 | 14 | Admin — Stock | Admin stock table + alerts | Low stock + near-expiry highlight. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 60 | Table screenshot. | High
43 | 15 | Admin — Staff | Doctor profile API | CRUD; link department & specialties. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 55 | Create doctor via API. | Medium
44 | 15 | Admin — Staff | Department/specialty linkage | Many-to-many or refs as per ERD. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 55 | Filters use relations. | Medium
45 | 15 | Admin — Staff | Admin staff management UI | Table + modal forms. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 50 | CRUD demo video. | Medium
46 | 16 | Doctor — Imaging | Cloudinary config | Env keys; secure upload preset. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 50 | Upload returns URL. | Medium
47 | 16 | Doctor — Imaging | Media linked to encounter | Store metadata; patient/doctor ACL. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 50 | Image tied to visit. | Medium
48 | 16 | Doctor — Imaging | Imaging gallery UI | Thumbnails; lightbox. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 40 | One X-ray uploaded. | Medium
49 | 17 | Admin — Facilities | Clinic room model | Functional room types; equipment notes. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 45 | Rooms under branch. | Standard
50 | 17 | Admin — Facilities | Room REST API | List/create/update for admin. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 40 | Postman collection. | Standard
51 | 17 | Admin — Facilities | Admin room list UI | Simple list + optional floor diagram URL. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 35 | Room layout diagram. | Standard
52 | 18 | Admin — Catalog | ICD collection + search | Index code + title; text search. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 35 | Search returns top 10. | Standard
53 | 18 | Admin — Catalog | CSV import script | Bulk load sample ICD rows. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 40 | Import sample CSV. | Standard
54 | 18 | Admin — Catalog | Diagnosis autocomplete UI | Doctor form uses search endpoint. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 25 | Pick code from list. | Standard
55 | 19 | Portal — Booking | Booking wizard state | Steps: department → doctor → slot. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | State machine or query params. | High
56 | 19 | Portal — Booking | Slot selection + summary | Show price/deposit if any before confirm. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | Summary step screenshot. | High
57 | 19 | Portal — Booking | Confirm booking API call | POST booking; handle errors. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 60 | Screen recording full flow. | High
58 | 20 | API Booking | Concurrency guard | Unique index or transaction on slot+doctor. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | 409 on double book. | High
59 | 20 | API Booking | Book API integration | Return clear error bodies. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 40 | Postman shows 409. | High
60 | 20 | API Booking | Parallel booking test | Two clients race for last seat. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 35 | Only one wins. | High
61 | 21 | Portal — Home | Featured blocks CMS or static | Services + doctors spotlight data. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | Content visible on home. | Medium
62 | 21 | Portal — Home | Health news strip | Optional JSON or markdown list. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | News cards render. | Medium
63 | 21 | Portal — Home | Responsive layout polish | Breakpoints; lazy images. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 40 | Mobile + desktop capture. | Medium
64 | 22 | Notifications | VAPID + subscription storage | Save endpoint + keys per user. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 50 | Row in DB after subscribe. | Medium
65 | 22 | Notifications | Server push sender | Helper to notify appointment reminder. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 50 | Trigger test push. | Medium
66 | 22 | Notifications | Client subscribe UX | Permission prompt; unsubscribe. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 40 | Chrome subscription demo. | Medium
67 | 23 | Portal — Review | Review model + uniqueness | One review per completed appointment. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 35 | 409 on duplicate. | Medium
68 | 23 | Portal — Review | Submit review API | Rating + comment validation. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 35 | API returns created review. | Medium
69 | 23 | Portal — Review | Post-visit review UI | Modal after checkout or email deep link. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 30 | One sample review. | Medium
70 | 24 | Portal — Favorites | Favorites API | Add/remove doctor for patient. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | List returns favorites. | Standard
71 | 24 | Portal — Favorites | Favorites page UI | Shortcuts to book again. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 35 | Add/remove favorite. | Standard
72 | 25 | Admin — Reports | Revenue aggregation | Mongo pipeline by day/month/branch. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 70 | JSON aggregates match seed. | High
73 | 25 | Admin — Reports | Chart.js dashboard | Bar/line for revenue trend. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 70 | Monthly dashboard screenshot. | High
74 | 25 | Admin — Reports | Report filters | Date range + export trigger. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Filter changes chart. | Medium
75 | 26 | Doctor — Prescriptions | HTML prescription template | Branding + table for meds/dosage. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 55 | Preview in browser. | High
76 | 26 | Doctor — Prescriptions | PDF render service | Puppeteer/pdf-lib or server lib from encounter. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 55 | Download PDF sample. | High
77 | 26 | Doctor — Prescriptions | Secure download route | Auth + short-lived token for PDF. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 50 | Doctor can download own Rx. | High
78 | 27 | Portal + Kiosk | Signed QR payload | Encode visit/Rx id + checksum. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | QR renders on screen. | Medium
79 | 27 | Portal + Kiosk | Verify API / kiosk page | Scan flow validates signature. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | Valid vs tampered demo. | Medium
80 | 27 | Portal + Kiosk | Mobile scan UX | Camera opens; deep link optional. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 30 | Phone camera demo. | Medium
81 | 28 | System — Email | SMTP transporter | Env-based config; HTML templates folder. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 45 | Send test mail. | Medium
82 | 28 | System — Email | Template triggers | After visit: results; Rx; follow-up date. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Correct template picked. | Medium
83 | 28 | System — Email | MailHog / log mode | Dev capture without real SMTP. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | MailHog inbox shows mail. | Medium
84 | 29 | Portal — Maps | Branch geo fields | lat/lng on clinic document. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 35 | Map centers correctly. | Medium
85 | 29 | Portal — Maps | Maps embed component | Google/Mapbox embed + directions link. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 35 | Directions open externally. | Medium
86 | 29 | Portal — Maps | Marker UX | Info window with hours/phone. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 30 | One marker demo. | Medium
87 | 30 | Admin + Portal | Complaint ticket model | Statuses: new/in_progress/resolved. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | State transitions. | Standard
88 | 30 | Admin + Portal | Admin triage UI | Kanban or table by status. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Admin updates status. | Standard
89 | 30 | Admin + Portal | Patient complaint form | Portal submit + list own tickets. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 30 | Ticket workflow. | Standard
90 | 31 | Server — Quality | Shared validators | Zod/Joi schemas colocated with routes. | Team | To Do | 1 | SRS § | SDS § | 50 | Reused across modules. | Medium
91 | 31 | Server — Quality | Wire validators on routers | Central registration pattern. | Team | To Do | 1 | SRS § | SDS § | 55 | Invalid body 400. | Medium
92 | 31 | Server — Quality | 400 demo collection | Postman examples for team. | Team | To Do | 1 | SRS § | SDS § | 45 | Example 400 body. | Medium
93 | 32 | Server — Quality | Error code enum + DTO | Consistent JSON error shape. | Team | To Do | 1 | SRS § | SDS § | 30 | Docs in README. | Medium
94 | 32 | Server — Quality | Global error middleware | Map errors to status; hide stack in prod. | Team | To Do | 1 | SRS § | SDS § | 30 | Prod vs dev behavior. | Medium
95 | 32 | Server — Quality | Postman error examples | Saved responses for common codes. | Team | To Do | 1 | SRS § | SDS § | 20 | Error shape demo. | Standard
96 | 33 | DevOps | Seed script content | Departments, rooms, sample users, ICD sample. | Team | To Do | 1 | SRS § | SDS § | 35 | DB populated after run. | Standard
97 | 33 | DevOps | npm run seed wiring | package.json script + idempotent upserts. | Team | To Do | 1 | SRS § | SDS § | 25 | Second run no dup errors. | Standard
98 | 34 | Docs | OpenAPI or endpoint table | All main routes listed. | Team | To Do | 1 | SRS § | SDS § | 25 | File committed under docs/. | Standard
99 | 34 | Docs | README link | Single link to contract from root README. | Team | To Do | 1 | SRS § | SDS § | 15 | Link works on GitHub. | Standard
100 | 35 | QA | Supertest: health + 404 | Smoke baseline. | Team | To Do | 4 | SRS § | SDS § | 35 | CI green on empty DB. | Medium
101 | 35 | QA | Supertest: auth + booking stub | Minimal happy path. | Team | To Do | 4 | SRS § | SDS § | 40 | Uses test DB. | Medium
102 | 35 | QA | CI workflow | GitHub Action runs tests on push. | Team | To Do | 4 | SRS § | SDS § | 25 | Badge optional. | Medium

## Sprint_1
# | Parent_ID | Screen_Function | Feature | Description | In_Charge | Status | Sprint | SRS | SDS | LOC | Code_Demo_Comments | Complexity | Quality
7 | 3 | Server — API architecture | Express structure | Routes/controllers/services layout; mount routers. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 45 | Folder tree matches SDS. | Medium
8 | 3 | Server — API architecture | Cross-cutting middleware | CORS, request logging, centralized error wrapper stub. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 45 | Logs show request id. | Medium
9 | 3 | Server — API architecture | JWT middleware scaffold + /health | Optional verify hook; GET /health + Mongo ping. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 30 | Health returns 200 when DB up. | Medium
49 | 17 | Admin — Facilities | Clinic room model | Functional room types; equipment notes. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 45 | Rooms under branch. | Standard
50 | 17 | Admin — Facilities | Room REST API | List/create/update for admin. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 40 | Postman collection. | Standard
51 | 17 | Admin — Facilities | Admin room list UI | Simple list + optional floor diagram URL. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 35 | Room layout diagram. | Standard
90 | 31 | Server — Quality | Shared validators | Zod/Joi schemas colocated with routes. | Team | To Do | 1 | SRS § | SDS § | 50 | Reused across modules. | Medium
91 | 31 | Server — Quality | Wire validators on routers | Central registration pattern. | Team | To Do | 1 | SRS § | SDS § | 55 | Invalid body 400. | Medium
92 | 31 | Server — Quality | 400 demo collection | Postman examples for team. | Team | To Do | 1 | SRS § | SDS § | 45 | Example 400 body. | Medium
93 | 32 | Server — Quality | Error code enum + DTO | Consistent JSON error shape. | Team | To Do | 1 | SRS § | SDS § | 30 | Docs in README. | Medium
94 | 32 | Server — Quality | Global error middleware | Map errors to status; hide stack in prod. | Team | To Do | 1 | SRS § | SDS § | 30 | Prod vs dev behavior. | Medium
95 | 32 | Server — Quality | Postman error examples | Saved responses for common codes. | Team | To Do | 1 | SRS § | SDS § | 20 | Error shape demo. | Standard
96 | 33 | DevOps | Seed script content | Departments, rooms, sample users, ICD sample. | Team | To Do | 1 | SRS § | SDS § | 35 | DB populated after run. | Standard
97 | 33 | DevOps | npm run seed wiring | package.json script + idempotent upserts. | Team | To Do | 1 | SRS § | SDS § | 25 | Second run no dup errors. | Standard
98 | 34 | Docs | OpenAPI or endpoint table | All main routes listed. | Team | To Do | 1 | SRS § | SDS § | 25 | File committed under docs/. | Standard
99 | 34 | Docs | README link | Single link to contract from root README. | Team | To Do | 1 | SRS § | SDS § | 15 | Link works on GitHub. | Standard

## Sprint_2
# | Parent_ID | Screen_Function | Feature | Description | In_Charge | Status | Sprint | SRS | SDS | LOC | Code_Demo_Comments | Complexity | Quality
10 | 4 | Portal + API | Register API | Validate payload; hash password; create user + role. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 55 | Invalid email returns 400. | Medium
11 | 4 | Portal + API | Login + JWT issue | Compare hash; sign access token; optional refresh stub. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 55 | Postman returns Bearer token. | Medium
12 | 4 | Portal + API | Client login/register UI | Forms, client validation, store token, redirect by role. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 40 | Short screen capture of flow. | Medium
16 | 6 | Portal — Profile | Profile GET/PATCH API | Own-profile only; partial updates. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 35 | 403 for other users’ ids. | Medium
17 | 6 | Portal — Profile | Avatar upload | Multipart or URL field; size/type validation. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 30 | Avatar updates in header. | Medium
18 | 6 | Portal — Profile | Profile form UI | React form + schema validation + success toast. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 25 | Validated form demo. | Standard
34 | 12 | Server — RBAC | Permission matrix constants | Role → allowed actions map in code. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 35 | Table in README or MD. | Standard
35 | 12 | Server — RBAC | requireRole middleware | Composable guards for routes. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 40 | 403 on wrong role. | Medium
36 | 12 | Server — RBAC | Resource ownership checks | EMR/stock examples; tests for happy/deny. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 25 | Matrix demo. | Standard

## Sprint_3
# | Parent_ID | Screen_Function | Feature | Description | In_Charge | Status | Sprint | SRS | SDS | LOC | Code_Demo_Comments | Complexity | Quality
4 | 2 | Admin / Doctor — Schedule | Shift / workday model | Link doctors to working hours and branch capacity. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 70 | Seed shifts visible in DB. | Medium
5 | 2 | Admin / Doctor — Schedule | Slot generation service | Generate non-overlapping slots from shifts; API for grid. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 70 | JSON grid for one week. | High
6 | 2 | Admin / Doctor — Schedule | Admin/Doctor slot calendar UI | Day/week grid; block invalid edits. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 60 | UI shows slot grid by day. | High
13 | 5 | Portal — Find doctor | Doctor search API | Filters: name, specialty, branch; pagination. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 35 | curl/Postman sample queries. | Medium
14 | 5 | Portal — Find doctor | Symptom / keyword index | Regex or text index for hints; debounced suggest endpoint. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 40 | Typeahead demo. | Medium
15 | 5 | Portal — Find doctor | Patient portal search page | List + filters UI wired to API. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 25 | UI matches wireframe. | Standard
43 | 15 | Admin — Staff | Doctor profile API | CRUD; link department & specialties. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 55 | Create doctor via API. | Medium
44 | 15 | Admin — Staff | Department/specialty linkage | Many-to-many or refs as per ERD. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 55 | Filters use relations. | Medium
45 | 15 | Admin — Staff | Admin staff management UI | Table + modal forms. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 50 | CRUD demo video. | Medium
52 | 18 | Admin — Catalog | ICD collection + search | Index code + title; text search. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 35 | Search returns top 10. | Standard
53 | 18 | Admin — Catalog | CSV import script | Bulk load sample ICD rows. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 40 | Import sample CSV. | Standard
54 | 18 | Admin — Catalog | Diagnosis autocomplete UI | Doctor form uses search endpoint. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 25 | Pick code from list. | Standard
55 | 19 | Portal — Booking | Booking wizard state | Steps: department → doctor → slot. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | State machine or query params. | High
56 | 19 | Portal — Booking | Slot selection + summary | Show price/deposit if any before confirm. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | Summary step screenshot. | High
57 | 19 | Portal — Booking | Confirm booking API call | POST booking; handle errors. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 60 | Screen recording full flow. | High
58 | 20 | API Booking | Concurrency guard | Unique index or transaction on slot+doctor. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | 409 on double book. | High
59 | 20 | API Booking | Book API integration | Return clear error bodies. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 40 | Postman shows 409. | High
60 | 20 | API Booking | Parallel booking test | Two clients race for last seat. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 35 | Only one wins. | High
61 | 21 | Portal — Home | Featured blocks CMS or static | Services + doctors spotlight data. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | Content visible on home. | Medium
62 | 21 | Portal — Home | Health news strip | Optional JSON or markdown list. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | News cards render. | Medium
63 | 21 | Portal — Home | Responsive layout polish | Breakpoints; lazy images. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 40 | Mobile + desktop capture. | Medium
70 | 24 | Portal — Favorites | Favorites API | Add/remove doctor for patient. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | List returns favorites. | Standard
71 | 24 | Portal — Favorites | Favorites page UI | Shortcuts to book again. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 35 | Add/remove favorite. | Standard
84 | 29 | Portal — Maps | Branch geo fields | lat/lng on clinic document. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 35 | Map centers correctly. | Medium
85 | 29 | Portal — Maps | Maps embed component | Google/Mapbox embed + directions link. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 35 | Directions open externally. | Medium
86 | 29 | Portal — Maps | Marker UX | Info window with hours/phone. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 30 | One marker demo. | Medium

## Sprint_4
# | Parent_ID | Screen_Function | Feature | Description | In_Charge | Status | Sprint | SRS | SDS | LOC | Code_Demo_Comments | Complexity | Quality
1 | 1 | Queue screen (patient + doctor) | Queue session & ticket API | REST: open session, issue ticket, persist current number. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 60 | Postman CRUD session + ticket. | Medium
2 | 1 | Queue screen (patient + doctor) | Patient queue display | Waiting-room UI; subscribe to updates (Socket or polling fallback). | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 70 | Number changes without refresh. | Medium
3 | 1 | Queue screen (patient + doctor) | Doctor Next + Socket.io broadcast | Doctor action advances queue; emit room event to patients. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 50 | Two browsers stay in sync. | High
19 | 7 | Payments | Payment provider config | MoMo/VNPay sandbox keys; create payment request DTO. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 80 | Sandbox intent created. | High
20 | 7 | Payments | Callback / webhook handler | Verify signature; idempotent update booking/wallet. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 80 | Replay callback once safely. | High
21 | 7 | Payments | Payment UI + test path | Redirect or QR step; show success/failure. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 60 | One successful sandbox transaction. | High
22 | 8 | Wallet + API | Wallet model & invariants | Balance field; non-negative rule at schema/service. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 70 | Unit: cannot go below zero. | High
23 | 8 | Wallet + API | Credit/debit operations | Mongo transaction or equivalent; audit lines. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 70 | Concurrent debits handled. | High
24 | 8 | Wallet + API | Wallet UI + API wiring | Show balance; list last movements on dashboard. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | UI matches balance after op. | Medium
25 | 9 | Portal — Health insurance | Insurance card CRUD | Store policy number, dates, coverage percent. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 55 | Create + read card. | Medium
26 | 9 | Portal — Health insurance | OCR hook (optional) | Upload image URL; stub or external OCR parse. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 55 | Parsed fields editable. | Medium
27 | 9 | Portal — Health insurance | Billing discount rule | Apply coverage when quoting booking price. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 50 | With/without insurance cases. | Medium
28 | 10 | Portal — History | Transactions list API | Paging, sort by date desc. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Page 2 works. | Medium
29 | 10 | Portal — History | Filters | By date range and type (top-up, payment, refund). | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Filtered JSON. | Medium
30 | 10 | Portal — History | Portal history view | Table + optional CSV export button. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 30 | Export optional. | Medium
31 | 11 | Booking + Wallet | Cancel policy engine | Deadline rules per appointment type. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 45 | Unit tests inside/outside window. | Medium
32 | 11 | Booking + Wallet | Wallet refund credit | Atomic credit linked to cancellation reason. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 45 | Balance increases correctly. | Medium
33 | 11 | Booking + Wallet | Cancel UI flows | Patient cancels; shows refund message. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Two demo cases. | Medium
37 | 13 | Doctor — EMR | Encounter CRUD | Create/list encounters by patient; link appointment. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 90 | Three encounters in DB. | High
38 | 13 | Doctor — EMR | Diagnosis entries | Add DX per encounter; ICD ref optional. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 90 | Timeline sorted by date. | High
39 | 13 | Doctor — EMR | Doctor EMR UI | Timeline + patient search + encounter detail panel. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 60 | Click-through demo. | High
40 | 14 | Admin — Stock | Stock & movement models | Medicine SKU, quantity, batch/expiry fields. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 70 | Models in Mongoose. | High
41 | 14 | Admin — Stock | Inbound/outbound flows | Adjust stock; link outbound to prescription later. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 70 | Stock delta correct. | High
42 | 14 | Admin — Stock | Admin stock table + alerts | Low stock + near-expiry highlight. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 60 | Table screenshot. | High
46 | 16 | Doctor — Imaging | Cloudinary config | Env keys; secure upload preset. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 50 | Upload returns URL. | Medium
47 | 16 | Doctor — Imaging | Media linked to encounter | Store metadata; patient/doctor ACL. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 50 | Image tied to visit. | Medium
48 | 16 | Doctor — Imaging | Imaging gallery UI | Thumbnails; lightbox. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 40 | One X-ray uploaded. | Medium
64 | 22 | Notifications | VAPID + subscription storage | Save endpoint + keys per user. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 50 | Row in DB after subscribe. | Medium
65 | 22 | Notifications | Server push sender | Helper to notify appointment reminder. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 50 | Trigger test push. | Medium
66 | 22 | Notifications | Client subscribe UX | Permission prompt; unsubscribe. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 40 | Chrome subscription demo. | Medium
67 | 23 | Portal — Review | Review model + uniqueness | One review per completed appointment. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 35 | 409 on duplicate. | Medium
68 | 23 | Portal — Review | Submit review API | Rating + comment validation. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 35 | API returns created review. | Medium
69 | 23 | Portal — Review | Post-visit review UI | Modal after checkout or email deep link. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 30 | One sample review. | Medium
72 | 25 | Admin — Reports | Revenue aggregation | Mongo pipeline by day/month/branch. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 70 | JSON aggregates match seed. | High
73 | 25 | Admin — Reports | Chart.js dashboard | Bar/line for revenue trend. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 70 | Monthly dashboard screenshot. | High
74 | 25 | Admin — Reports | Report filters | Date range + export trigger. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Filter changes chart. | Medium
75 | 26 | Doctor — Prescriptions | HTML prescription template | Branding + table for meds/dosage. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 55 | Preview in browser. | High
76 | 26 | Doctor — Prescriptions | PDF render service | Puppeteer/pdf-lib or server lib from encounter. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 55 | Download PDF sample. | High
77 | 26 | Doctor — Prescriptions | Secure download route | Auth + short-lived token for PDF. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 50 | Doctor can download own Rx. | High
78 | 27 | Portal + Kiosk | Signed QR payload | Encode visit/Rx id + checksum. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | QR renders on screen. | Medium
79 | 27 | Portal + Kiosk | Verify API / kiosk page | Scan flow validates signature. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | Valid vs tampered demo. | Medium
80 | 27 | Portal + Kiosk | Mobile scan UX | Camera opens; deep link optional. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 30 | Phone camera demo. | Medium
81 | 28 | System — Email | SMTP transporter | Env-based config; HTML templates folder. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 45 | Send test mail. | Medium
82 | 28 | System — Email | Template triggers | After visit: results; Rx; follow-up date. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Correct template picked. | Medium
83 | 28 | System — Email | MailHog / log mode | Dev capture without real SMTP. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | MailHog inbox shows mail. | Medium
87 | 30 | Admin + Portal | Complaint ticket model | Statuses: new/in_progress/resolved. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | State transitions. | Standard
88 | 30 | Admin + Portal | Admin triage UI | Kanban or table by status. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Admin updates status. | Standard
89 | 30 | Admin + Portal | Patient complaint form | Portal submit + list own tickets. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 30 | Ticket workflow. | Standard
100 | 35 | QA | Supertest: health + 404 | Smoke baseline. | Team | To Do | 4 | SRS § | SDS § | 35 | CI green on empty DB. | Medium
101 | 35 | QA | Supertest: auth + booking stub | Minimal happy path. | Team | To Do | 4 | SRS § | SDS § | 40 | Uses test DB. | Medium
102 | 35 | QA | CI workflow | GitHub Action runs tests on push. | Team | To Do | 4 | SRS § | SDS § | 25 | Badge optional. | Medium