## LOC_OrcaXCare
LOC Evaluation for OrcaXCare (WDP301)
Columns A–K: # through LOC (subtasks). B = Parent epic id (1–35). H = Sprint (1–4).
Teacher fills columns L–N (Code Demo Comments, Complexity, Quality); pivot by In Charge for LOC totals.
# | Parent | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Sprint | SRS | SDS | LOC | Code Demo Comments | Complexity | Quality
1 | 1 | Queue screen (patient + doctor) | Queue session & ticket API | REST: open session, issue ticket, persist current number. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 60 | Medium: Postman CRUD session + ticket. | Medium
2 | 1 | Queue screen (patient + doctor) | Patient queue display | Waiting-room UI; subscribe to updates (Socket or polling fallback). | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 70 | Medium: Number changes without refresh. | Medium
3 | 1 | Queue screen (patient + doctor) | Doctor Next + Socket.io broadcast | Doctor action advances queue; emit room event to patients. | TruongNTCE180140 | To Do | 4 | SRS § | SDS § | 50 | Complex: Two browsers stay in sync. | High
4 | 2 | Admin / Doctor — Schedule | Shift / workday model | Link doctors to working hours and branch capacity. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 70 | Medium: Seed shifts visible in DB. | Medium
5 | 2 | Admin / Doctor — Schedule | Slot generation service | Generate non-overlapping slots from shifts; API for grid. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 70 | Complex: JSON grid for one week. | High
6 | 2 | Admin / Doctor — Schedule | Admin/Doctor slot calendar UI | Day/week grid; block invalid edits. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 60 | Complex: UI shows slot grid by day. | High
7 | 3 | Server — API architecture | Express structure | Routes/controllers/services layout; mount routers. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 45 | Medium: Folder tree matches SDS. | Medium
8 | 3 | Server — API architecture | Cross-cutting middleware | CORS, request logging, centralized error wrapper stub. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 45 | Medium: Logs show request id. | Medium
9 | 3 | Server — API architecture | JWT middleware scaffold + /health | Optional verify hook; GET /health + Mongo ping. | TruongNTCE180140 | To Do | 1 | SRS § | SDS § | 30 | Medium: Health returns 200 when DB up. | Medium
10 | 4 | Portal + API | Register API | Validate payload; hash password; create user + role. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 55 | Medium: Invalid email returns 400. | Medium
11 | 4 | Portal + API | Login + JWT issue | Compare hash; sign access token; optional refresh stub. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 55 | Medium: Postman returns Bearer token. | Medium
12 | 4 | Portal + API | Client login/register UI | Forms, client validation, store token, redirect by role. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 40 | Medium: Short screen capture of flow. | Medium
13 | 5 | Portal — Find doctor | Doctor search API | Filters: name, specialty, branch; pagination. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 35 | Medium: curl/Postman sample queries. | Medium
14 | 5 | Portal — Find doctor | Symptom / keyword index | Regex or text index for hints; debounced suggest endpoint. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 40 | Medium: Typeahead demo. | Medium
15 | 5 | Portal — Find doctor | Patient portal search page | List + filters UI wired to API. | TruongNTCE180140 | To Do | 3 | SRS § | SDS § | 25 | Simple: UI matches wireframe. | Standard
16 | 6 | Portal — Profile | Profile GET/PATCH API | Own-profile only; partial updates. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 35 | Medium: 403 for other users’ ids. | Medium
17 | 6 | Portal — Profile | Avatar upload | Multipart or URL field; size/type validation. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 30 | Medium: Avatar updates in header. | Medium
18 | 6 | Portal — Profile | Profile form UI | React form + schema validation + success toast. | TruongNTCE180140 | To Do | 2 | SRS § | SDS § | 25 | Simple: Validated form demo. | Standard
19 | 7 | Payments | Payment provider config | MoMo/VNPay sandbox keys; create payment request DTO. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 80 | Complex: Sandbox intent created. | High
20 | 7 | Payments | Callback / webhook handler | Verify signature; idempotent update booking/wallet. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 80 | Complex: Replay callback once safely. | High
21 | 7 | Payments | Payment UI + test path | Redirect or QR step; show success/failure. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 60 | Complex: One successful sandbox transaction. | High
22 | 8 | Wallet + API | Wallet model & invariants | Balance field; non-negative rule at schema/service. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 70 | Complex: Unit: cannot go below zero. | High
23 | 8 | Wallet + API | Credit/debit operations | Mongo transaction or equivalent; audit lines. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 70 | Complex: Concurrent debits handled. | High
24 | 8 | Wallet + API | Wallet UI + API wiring | Show balance; list last movements on dashboard. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Medium: UI matches balance after op. | Medium
25 | 9 | Portal — Health insurance | Insurance card CRUD | Store policy number, dates, coverage percent. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 55 | Medium: Create + read card. | Medium
26 | 9 | Portal — Health insurance | OCR hook (optional) | Upload image URL; stub or external OCR parse. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 55 | Medium: Parsed fields editable. | Medium
27 | 9 | Portal — Health insurance | Billing discount rule | Apply coverage when quoting booking price. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 50 | Medium: With/without insurance cases. | Medium
28 | 10 | Portal — History | Transactions list API | Paging, sort by date desc. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Medium: Page 2 works. | Medium
29 | 10 | Portal — History | Filters | By date range and type (top-up, payment, refund). | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Medium: Filtered JSON. | Medium
30 | 10 | Portal — History | Portal history view | Table + optional CSV export button. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 30 | Medium: Export optional. | Medium
31 | 11 | Booking + Wallet | Cancel policy engine | Deadline rules per appointment type. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 45 | Medium: Unit tests inside/outside window. | Medium
32 | 11 | Booking + Wallet | Wallet refund credit | Atomic credit linked to cancellation reason. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 45 | Medium: Balance increases correctly. | Medium
33 | 11 | Booking + Wallet | Cancel UI flows | Patient cancels; shows refund message. | TanhNTCE182341 | To Do | 4 | SRS § | SDS § | 40 | Medium: Two demo cases. | Medium
34 | 12 | Server — RBAC | Permission matrix constants | Role → allowed actions map in code. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 35 | Simple: Table in README or MD. | Standard
35 | 12 | Server — RBAC | requireRole middleware | Composable guards for routes. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 40 | Medium: 403 on wrong role. | Medium
36 | 12 | Server — RBAC | Resource ownership checks | EMR/stock examples; tests for happy/deny. | TanhNTCE182341 | To Do | 2 | SRS § | SDS § | 25 | Simple: Matrix demo. | Standard
37 | 13 | Doctor — EMR | Encounter CRUD | Create/list encounters by patient; link appointment. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 90 | Complex: Three encounters in DB. | High
38 | 13 | Doctor — EMR | Diagnosis entries | Add DX per encounter; ICD ref optional. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 90 | Complex: Timeline sorted by date. | High
39 | 13 | Doctor — EMR | Doctor EMR UI | Timeline + patient search + encounter detail panel. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 60 | Complex: Click-through demo. | High
40 | 14 | Admin — Stock | Stock & movement models | Medicine SKU, quantity, batch/expiry fields. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 70 | Complex: Models in Mongoose. | High
41 | 14 | Admin — Stock | Inbound/outbound flows | Adjust stock; link outbound to prescription later. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 70 | Complex: Stock delta correct. | High
42 | 14 | Admin — Stock | Admin stock table + alerts | Low stock + near-expiry highlight. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 60 | Complex: Table screenshot. | High
43 | 15 | Admin — Staff | Doctor profile API | CRUD; link department & specialties. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 55 | Medium: Create doctor via API. | Medium
44 | 15 | Admin — Staff | Department/specialty linkage | Many-to-many or refs as per ERD. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 55 | Medium: Filters use relations. | Medium
45 | 15 | Admin — Staff | Admin staff management UI | Table + modal forms. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 50 | Medium: CRUD demo video. | Medium
46 | 16 | Doctor — Imaging | Cloudinary config | Env keys; secure upload preset. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 50 | Medium: Upload returns URL. | Medium
47 | 16 | Doctor — Imaging | Media linked to encounter | Store metadata; patient/doctor ACL. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 50 | Medium: Image tied to visit. | Medium
48 | 16 | Doctor — Imaging | Imaging gallery UI | Thumbnails; lightbox. | ThangNDCE180608 | To Do | 4 | SRS § | SDS § | 40 | Medium: One X-ray uploaded. | Medium
49 | 17 | Admin — Facilities | Clinic room model | Functional room types; equipment notes. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 45 | Simple: Rooms under branch. | Standard
50 | 17 | Admin — Facilities | Room REST API | List/create/update for admin. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 40 | Simple: Postman collection. | Standard
51 | 17 | Admin — Facilities | Admin room list UI | Simple list + optional floor diagram URL. | ThangNDCE180608 | To Do | 1 | SRS § | SDS § | 35 | Simple: Room layout diagram. | Standard
52 | 18 | Admin — Catalog | ICD collection + search | Index code + title; text search. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 35 | Simple: Search returns top 10. | Standard
53 | 18 | Admin — Catalog | CSV import script | Bulk load sample ICD rows. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 40 | Simple: Import sample CSV. | Standard
54 | 18 | Admin — Catalog | Diagnosis autocomplete UI | Doctor form uses search endpoint. | ThangNDCE180608 | To Do | 3 | SRS § | SDS § | 25 | Simple: Pick code from list. | Standard
55 | 19 | Portal — Booking | Booking wizard state | Steps: department → doctor → slot. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | Complex: State machine or query params. | High
56 | 19 | Portal — Booking | Slot selection + summary | Show price/deposit if any before confirm. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 80 | Complex: Summary step screenshot. | High
57 | 19 | Portal — Booking | Confirm booking API call | POST booking; handle errors. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 60 | Complex: Screen recording full flow. | High
58 | 20 | API Booking | Concurrency guard | Unique index or transaction on slot+doctor. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | Complex: 409 on double book. | High
59 | 20 | API Booking | Book API integration | Return clear error bodies. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 40 | Complex: Postman shows 409. | High
60 | 20 | API Booking | Parallel booking test | Two clients race for last seat. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 35 | Complex: Only one wins. | High
61 | 21 | Portal — Home | Featured blocks CMS or static | Services + doctors spotlight data. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | Medium: Content visible on home. | Medium
62 | 21 | Portal — Home | Health news strip | Optional JSON or markdown list. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | Medium: News cards render. | Medium
63 | 21 | Portal — Home | Responsive layout polish | Breakpoints; lazy images. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 40 | Medium: Mobile + desktop capture. | Medium
64 | 22 | Notifications | VAPID + subscription storage | Save endpoint + keys per user. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 50 | Medium: Row in DB after subscribe. | Medium
65 | 22 | Notifications | Server push sender | Helper to notify appointment reminder. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 50 | Medium: Trigger test push. | Medium
66 | 22 | Notifications | Client subscribe UX | Permission prompt; unsubscribe. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 40 | Medium: Chrome subscription demo. | Medium
67 | 23 | Portal — Review | Review model + uniqueness | One review per completed appointment. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 35 | Medium: 409 on duplicate. | Medium
68 | 23 | Portal — Review | Submit review API | Rating + comment validation. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 35 | Medium: API returns created review. | Medium
69 | 23 | Portal — Review | Post-visit review UI | Modal after checkout or email deep link. | ThangDQCE182036 | To Do | 4 | SRS § | SDS § | 30 | Medium: One sample review. | Medium
70 | 24 | Portal — Favorites | Favorites API | Add/remove doctor for patient. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 45 | Simple: List returns favorites. | Standard
71 | 24 | Portal — Favorites | Favorites page UI | Shortcuts to book again. | ThangDQCE182036 | To Do | 3 | SRS § | SDS § | 35 | Simple: Add/remove favorite. | Standard
72 | 25 | Admin — Reports | Revenue aggregation | Mongo pipeline by day/month/branch. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 70 | Complex: JSON aggregates match seed. | High
73 | 25 | Admin — Reports | Chart.js dashboard | Bar/line for revenue trend. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 70 | Complex: Monthly dashboard screenshot. | High
74 | 25 | Admin — Reports | Report filters | Date range + export trigger. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Medium: Filter changes chart. | Medium
75 | 26 | Doctor — Prescriptions | HTML prescription template | Branding + table for meds/dosage. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 55 | Complex: Preview in browser. | High
76 | 26 | Doctor — Prescriptions | PDF render service | Puppeteer/pdf-lib or server lib from encounter. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 55 | Complex: Download PDF sample. | High
77 | 26 | Doctor — Prescriptions | Secure download route | Auth + short-lived token for PDF. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 50 | Complex: Doctor can download own Rx. | High
78 | 27 | Portal + Kiosk | Signed QR payload | Encode visit/Rx id + checksum. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | Medium: QR renders on screen. | Medium
79 | 27 | Portal + Kiosk | Verify API / kiosk page | Scan flow validates signature. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | Medium: Valid vs tampered demo. | Medium
80 | 27 | Portal + Kiosk | Mobile scan UX | Camera opens; deep link optional. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 30 | Medium: Phone camera demo. | Medium
81 | 28 | System — Email | SMTP transporter | Env-based config; HTML templates folder. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 45 | Medium: Send test mail. | Medium
82 | 28 | System — Email | Template triggers | After visit: results; Rx; follow-up date. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Medium: Correct template picked. | Medium
83 | 28 | System — Email | MailHog / log mode | Dev capture without real SMTP. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 35 | Medium: MailHog inbox shows mail. | Medium
84 | 29 | Portal — Maps | Branch geo fields | lat/lng on clinic document. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 35 | Medium: Map centers correctly. | Medium
85 | 29 | Portal — Maps | Maps embed component | Google/Mapbox embed + directions link. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 35 | Medium: Directions open externally. | Medium
86 | 29 | Portal — Maps | Marker UX | Info window with hours/phone. | KhoaNNCE181612 | To Do | 3 | SRS § | SDS § | 30 | Medium: One marker demo. | Medium
87 | 30 | Admin + Portal | Complaint ticket model | Statuses: new/in_progress/resolved. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Simple: State transitions. | Standard
88 | 30 | Admin + Portal | Admin triage UI | Kanban or table by status. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 40 | Simple: Admin updates status. | Standard
89 | 30 | Admin + Portal | Patient complaint form | Portal submit + list own tickets. | KhoaNNCE181612 | To Do | 4 | SRS § | SDS § | 30 | Simple: Ticket workflow. | Standard
90 | 31 | Server — Quality | Shared validators | Zod/Joi schemas colocated with routes. | Team | To Do | 1 | SRS § | SDS § | 50 | Medium: Reused across modules. | Medium
91 | 31 | Server — Quality | Wire validators on routers | Central registration pattern. | Team | To Do | 1 | SRS § | SDS § | 55 | Medium: Invalid body 400. | Medium
92 | 31 | Server — Quality | 400 demo collection | Postman examples for team. | Team | To Do | 1 | SRS § | SDS § | 45 | Medium: Example 400 body. | Medium
93 | 32 | Server — Quality | Error code enum + DTO | Consistent JSON error shape. | Team | To Do | 1 | SRS § | SDS § | 30 | Medium: Docs in README. | Medium
94 | 32 | Server — Quality | Global error middleware | Map errors to status; hide stack in prod. | Team | To Do | 1 | SRS § | SDS § | 30 | Medium: Prod vs dev behavior. | Medium
95 | 32 | Server — Quality | Postman error examples | Saved responses for common codes. | Team | To Do | 1 | SRS § | SDS § | 20 | Simple: Error shape demo. | Standard
96 | 33 | DevOps | Seed script content | Departments, rooms, sample users, ICD sample. | Team | To Do | 1 | SRS § | SDS § | 35 | Simple: DB populated after run. | Standard
97 | 33 | DevOps | npm run seed wiring | package.json script + idempotent upserts. | Team | To Do | 1 | SRS § | SDS § | 25 | Simple: Second run no dup errors. | Standard
98 | 34 | Docs | OpenAPI or endpoint table | All main routes listed. | Team | To Do | 1 | SRS § | SDS § | 25 | Simple: File committed under docs/. | Standard
99 | 34 | Docs | README link | Single link to contract from root README. | Team | To Do | 1 | SRS § | SDS § | 15 | Simple: Link works on GitHub. | Standard
100 | 35 | QA | Supertest: health + 404 | Smoke baseline. | Team | To Do | 4 | SRS § | SDS § | 35 | Medium: CI green on empty DB. | Medium
101 | 35 | QA | Supertest: auth + booking stub | Minimal happy path. | Team | To Do | 4 | SRS § | SDS § | 40 | Medium: Uses test DB. | Medium
102 | 35 | QA | CI workflow | GitHub Action runs tests on push. | Team | To Do | 4 | SRS § | SDS § | 25 | Medium: Badge optional. | Medium